## DEPT
KSOM DEPARTMENT CLOSEOUT CHECKLIST FOR SPONSORED PROJECTS
This checklist tool is to aid in the timely wind-down and closeout of grant accounts.
Please review the tasks shown and associated timeframes in order to anticipate what will be required.
There may be additional tasks needed. Review the award terms and add tasks as needed in the spaces provided.
PI: |  |  | USC AWD #:
Project/ Research Admin. |  |  | Sponsor Award ID:
Unit: |  |  | Project End Date:
Timeline | Task | Completed or NA | Completed Date | Comments
120 DAYS PRIOR TO AWARD END DATE
Communicate with internal stakeholders that project is ending: PI, Project Administration
Review award Terms and Conditions for any unusual deliverables or reporting requirements
Review budget balances and projections, including cost share accounts
Review subawards
Review outstanding invoices, open POs
90 DAYS PRIOR TO AWARD END DATE
Notify Subcontracts that PRIME award will be closing and ask for a final projection for remaining invoices
| Work with PI to create a Final Spending Plan or projections for all chartstrings associated with the award |  |  | Review every project opened up under the award (i.e., satellite accounts)
| Review Payroll and stipend charges currently on grant and determine future funding sources |  |  | Starting from May 1, 2024, the KSOM staff must be given a 60-day notice prior to their termination resulting from the end of grant, contract or gift funding. This means that any terminations due to funding, with an effective date from May 1, 2024 to August 31, 2024, will be subject to this 60-day notice requirement. Attached please find the end of funding notice for reference during this period.
| If any program income exists, inform SPA. |  |  | Example: income from fees for services performed, charges for the use or rental of equipment or supplies acquired under the grant, the sale of commodities or items fabricated under an award, charges for research resources, or registration fees for grant-supported conferences
| If there is cost sharing, ensure that commitments have been met and funded. Ensure all expenses are allowable. |  |  | All cost shared effort must be certified in the Effort Reporting System.
Work with IACUC and IRB to transfer protocols, if appropriate.
For NSF, review Participant Support Cost budget and expenditures. Rebudgeting of unspent Participant Support budget is not allowed without prior approval.
Verify that all expenses are allowable, especially those posted within the last three months of the award. Items such as capital equipment purchases, service contracts, and large supply purchases are generally not allowable during the last three months of an award.
Review research subject payments and ensure expenses have been posted to the grant.
30 DAYS PRIOR TO AWARD END DATE
Notify research staff and students that award is ending so they stop using the account at the appropriate time.
| Notify University Services and recharge centers to stop using the account after the current month's charges are submitted in order to avoid post-award correction journals. |  |  | Common recurring expenses are lab gasses and tank rentals.
Review final spending plan and identify pending expenses that will need to post before end of award (e.g., travel, PAAs)
Begin to close out all Blanket Orders. Final expenses should be made on Purchase Orders and must be received before the award end date.
Review open encumbrances and expenses that are not posted (purchase orders, travel expense reports). Delete any invalid or obsolete encumbrances in Workday.
Resolve effort-related issues.
AFTER PROJECT END DATE- Steps should ideally be completed in order listed.
Respond and resolve highlighted expense review items identified by SPA.
Verify that all encumbrances have cleared.
Confirm all expenses have posted.
Ask SPPA to inactivate all expense account codes for which no additional expenses are expected (e.g. payroll, recurring expenses, supplies, travel, etc.), to prevent unwanted expenses being charged. Once all trailing expenses have been posted, send another email to the SPA to inactivate all expense codes on the project.
If any salary has not posted, notify SPA to extend project end date.
| If there are subcontracts, ensure that Final invoice has been received and paid. Also verify that the final report has been submitted to the PI. |  |  | Due by ~ 45 days after award ends.
| Verify that PI has submitted final technical report to sponsor. Federal award technical reports must be submitted within 90 days of end date. |  |  | Questions regarding these reports should be directed to the DCG Officer. Ask PI for a copy of the technical report.
Verify that PI has submitted other required reports (Invention report, etc.)
| If there is an overdraft after all valid transactions have posted, there are three options: 1) Issue correction journals to move specific expenses to a non-sponsored account 2) Inform SPA that the deficit will be covered by a non-sponsored account and provide altenrate account to SPA 3) If the cost share requirement has not been met, issue correction journals to move expenses between funds within the project. |  |  | Note that payroll charges must be moved to non-sponsored account via a PAA.
After the Department has completed all its tasks, send an email to the SPA requesting to initiate the closeout process.
If there is Program Income, send Program Income Statement to SPA and cc the DCG Officer via email.
JAS:5_3_24